## Sheet1
DEFECT ID | MODULE NAME | DEFECT SUMMARY | DEFECT DESCRIPTION | DEFECT CATEGORY | DEFECTED IN BROWSER | ENVIRONMENT | DEFECT SEVERITY | DEFECT PRIORITY | DEFECTED IN RELEASE # | DEFECTED IN BUILD # | REPORTED DATE | REPORTED BY | ASSIGNED TO | STATUS | REVIEW TYPE/TEST CYCLE | TEST CASE NO. | FIXED BY | FIXED DATE | VERIFIED DATE | VERIFIED BY | VERIFIED IN RELEASE # | VERIFIED IN BUILD # | ATTACHEMENTS | COMMENTS
DF_001 | ADD TO CART | The Adding Product i.e "ADD(+)" button is found unable to increase the quantity of the product in the Add To Cart field. | Detailed Description: The Adding Product quantity i.e "ADD(+)" button is found unable to add a product in the Add To Cart field when user is actually trying to increase the quantity of the product. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. View the product 4.Click on Add To Cart button. 5)Click on "ADD(+)" button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to increase the quantity of the number of products as expected. The application stays on the same page. | Coding | Google Chrome |  | P1 | High | 1.1.2 | 2 | 24/11/2018 | Rajib Ghosh | Bilwa Pelapkar | ACT |  | TC_003 | Bilwa Pelapkar | 26/11/2018 | 26/11/2018 | Rajib Ghosh
DF_002 | ADD TO CART | The Adding Product i.e " REMOVE(-)" button is found unable to decrease the quantity of the product in the Add To Cart field. | Detailed Description: The Removing Product quantity i.e "REMOVE(-)" button is found unable to delete a product quantity in the Add To Cart when user is trying to decrease the quantity of the product. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. View the product 4.Click on Add To Cart button. 5)Click on "REMOVE(-)" button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to decrease the quantity of the number of products as expected. The application stays on the same page. | Coding | Google Chrome |  | P1 | High | 1.1.2 | 2 | 24/11/2018 | Chinmayee Khadapkar | Kavita Maurya | ACT |  | TC_004 | Kavita Maurya | 26/11/2018 | 26/11/2018 | Chinmayee Khedapkar
DF_003 | Add To Cart | The "Remove From Cart" button is found unable to delete the product from Add To Cart field. | Detailed Description: The "Remove From Cart" button is found unable to delete the product from Add To Cart field. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. View the product 4.Click on Add To Cart button. 5)Click on "Remove From Cart" button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to delete the product from the Add To Cart Field as expected. The application stays on the same page. | Coding | Google Chrome |  | P1 | High | 1.1.2 | 2 | 24/11/2018 | Chinmayee Khadapkar | Kavita Maurya | ACT |  | TC_005 | Kavita Maurya | 26/11/2018 | 26/11/2018 | Chinmayee Khedapkar
DF_004 | HOME | The "SIGN IN" button on the home page is found unable to navigate user to the sigin page . | Detailed Description: The "SIGN IN" button is found unable to navigate user to the sigin page where user can login with their valid credentials in the website. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3.Home is displayed. 4.User clicks on sigin button. 5.User is navigated to the sigin page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to navigate user on sigin page which is not as expected. | Coding | Google Chrome |  | P1 | High | 1.1.2 | 2 | 24/11/2018 | Bilwa Pelapkar | Kavita Maurya | ACT |  |  | Kavita Maurya | 26/11/2018 | 26/11/2018 | Bilwa Pelapkar
DF_005 | PAYMENT | The "UPDATE " button on Payment page is found unable to navigate user to the YOUR ADDRESS page for updation or addition of address for the shipping purpose. | Detailed Description: The "UPDATE " button on Payment page is found unable to navigate user to the YOUR ADDRESS page for updation or addition of address for the shipping purpose.The shipping address helps the Shipping agents to track users location. Steps To reproduce the bug: 1. Login to website. 2.Add product to cart. 3.Click on "UPDTAE" button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to navigate user on YOUR ADDRESS page which is not as expected. | Coding | Google Chrome |  | P1 | High | 1.1.2 | 2 | 24/11/2018 | Rajib Ghosh | Kavita Maurya | ACT |  | TC_010 | Kavita Maurya | 26/11/2018 | 26/11/2018 | Rajib Ghosh
DF_006 | PAYMENT | The "ADD ADDRESS " button on Payment page is found unable to navigate user to the YOUR ADDRESS page for updation or addition of address for the shipping purpose. | Detailed Description: The "ADD ADDRESS " button on Payment page is found unable to navigate user to the YOUR ADDRESS page for updation or addition of address for the shipping purpose.The shipping address helps the Shipping agents to track users location. Steps To reproduce the bug: 1. Login to website. 2.Add product to cart. 3.Click on "ADD ADDRESS" button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to navigate user on YOUR ADDRESS page which is not as expected. | Coding | Google Chrome |  | P1 | High | 1.1.2 | 2 | 24/11/2018 | Rajib Ghosh | Kavita Maurya | ACT |  | TC_011 | Kavita Maurya | 26/11/2018 | 26/11/2018 | Rajib Ghosh
DF_007 | PAYMENT | The "Continue shopping " button on ADD TO CART page is found unable to navigate user to the Home page. | Detailed Description: The "Continue shopping " button is found unable to navigate user to the Home pagewhich restricts user to add more product in cart. Steps To reproduce the bug: 1. Login to website. 2.Add product to cart. 3.Click on "Continue shopping" button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to navigate user on home page which is not as expected. | Coding | Google Chrome |  | P1 | High | 1.1.2 | 2 | 24/11/2018 | Rajib Ghosh | Kavita Maurya | ACT |  | TC_012 | Kavita Maurya | 26/11/2018 | 26/11/2018 | Rajib Ghosh
DF_008 | PAYMENT | The "Proceed Checkout " button on My cart page is found unable to navigate user to the payment page. | Detailed Description: The "Proceed checkout " button is found unable to navigate user to the payment page which restricts user to proceed further for the payment. Steps To reproduce the bug: 1. Login to website. 2.Add product to cart. 3.Click on "Proceed checkout" button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to navigate user on payment page which is not as expected. | Design | Google Chrome |  | P1 | High | 1.1.2 | 2 | 24/11/2018 | Rajib Ghosh | Kavita Maurya | ACT |  | TC_013 | Kavita Maurya | 26/11/2018 | 26/11/2018 | Rajib Ghosh
DF_009 | Payment | The payment gateway is found not able to search the order reference number directly through the website which is to be render from the order details page. | Detailed Description: The sigin button on the home page is found not to be functional. Steps To reproduce the bug: 1.Login to the website. 2.Add product to the cart. 3.Enter your address. 4.Enter your shipping address. 5.Choose bank wire as payment option. 6.Click on "I confirm my order" Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to detect the order reference number from the website to bank wire | Coding | Google Chrome |  | P1 | High | 1.1.2 | 2 | 24/11/2018 | Kavita Maurya | Rajib Ghosh | ACT |  | TC_017 | Rajib Ghosh | 26/11/2018 | 26/11/2018 | Kavita Maurya
DF_010 | LOGIN | The user is found not able to login in the website even on having a valid credentials for login. | Detailed Description: The user is found not able to login in the website even on having a valid credentials for login after clicking on sigin button. Steps To reproduce the bug: 1. Open URL "www.automationpractice.com" 2.Click on "Sign in" 3.Enter username and password. 4.Click on "Sign in" button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to navigate user on home page even on emtering the valid credentials. | Coding | Google Chrome |  | P1 | High | 1.1.2 | 2 | 24/11/2018 | Kavita Maurya | Chinmayee Khapadkar | ACT |  | TC_021 | Chinmayee Khapadkar | 26/11/2018 | 26/11/2018 | Kavita Maurya
DF_010 | LOGIN | The user is found to sigin even on keeping the firstname field blank while creating an account on the website. | Detailed Description: The user is found to sigin even on keeping the firstname field blank and other relevant data filled which allows user to directly login without any username. Steps To reproduce the bug: 1. Open URL "www.automationpractice.com" 2.Click on "Sign in" 3.Enter email address and click on"Create an account". 4.Fill all relevant data and keep first name blank. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to error message to user for blank first name field which is nor as expected. | Coding | Google Chrome |  | P1 | High | 1.1.2 | 2 | 24/11/2018 | Kavita Maurya | Chinmayee Khapadkar | ACT |  | TC_024 | Chinmayee Khapadkar | 26/11/2018 | 26/11/2018 | Kavita Maurya
DF_011 | LOGIN | The password field on Account creation page is found to be accepting password less than 5 characters. | Detailed Description: The password field on Account creation page is found to be accepting password less than 5 characters voilating the actual bussiness need. Steps To reproduce the bug: 1. Open URL "www.automationpractice.com" 2.Click on "Sign in" 3.Enter email address and click on"Create an account". 4.Fill all relevant data andenter the password and click on "SUBMIT". Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to error message to user for entering more than 5 characters which is not as expected, | Coding | Google Chrome |  | P1 | High | 1.1.2 | 2 | 24/11/2018 | Kavita Maurya | Bineet Jaiswal | ACT |  | TC_025 | Bineet Jaiswal | 26/11/2018 | 26/11/2018 | Kavita Maurya
DF_012 | LOGIN | The zip code field on creating an account form is found to be accepting any type alphanumberic number. | Detailed Description: The zip code field is found to be accepting any fie alphanumberic number but zipcode must cintains only digits. Steps To reproduce the bug: 1. Open URL "www.automationpractice.com" 2.Click on "Sign in" 3.Enter email address and click on"Create an account". 4.Fill all relevant data andenter the zipcode and click on "SUBMIT". Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to error message to user for entering invalid zipcode value. | Coding | Google Chrome |  | P1 | High | 1.1.2 | 2 | 24/11/2018 | Kavita Maurya | Bineet Jaiswal | ACT |  | TC_027 | Bineet Jaiswal | 26/11/2018 | 26/11/2018 | Kavita Maurya
DF_013 | PAYMENT | The checkbox for the terms and conditions on the payment page is found disabled and non functional. | Detailed Description: The checkbox for the terms and conditions is found disabled and non functional which volatiles the security terms. Steps To reproduce the bug: 1.Login to the website. 2.Add product to cart. 3,Proceed to payment by clicking "Proceed checkout". 4.Click on I accept terms n condition. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable check the check box which is not as expected. | Coding | Google Chrome |  | P1 | High | 1.1.2 | 2 | 24/11/2018 | Bineet Jaiswal | Rajib Ghosh | ACT |  | TC_029 | Rajib Ghosh | 26/11/2018 | 26/11/2018 | Bineet Jaiswal
DF_014 | LOGIN | The potal is found not to be accepting the valid credentials of the user when user is trying to login to the website. | Detailed Description: When user enteres a valid credentials it is found that the user is not able to login in. Instead system is throwing an error for valid credentials. Steps To reproduce the bug: 1.Open url "automationpractice.com". 2.Click on Sigin. 3.Enter Username and Password. 4.Click on "SIGN IN" button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to navigate the user to the account page of the user which is not as expected. | Coding | Google Chrome |  | P1 | High | 1.1.1 |  | 24/11/2018 | Kavita Maurya | Bilwa Pelapkar | ACT |  | TC_008 | Bilwa Pelapkar | 26/11/2018 | 26/11/2018 | Kavita Maurya
DF_015 | HOME | The images on imageslider which is present on the home page is found not to be auto scrolling and remains static on the page. | Detailed Description: The images on imageslider which is present on the home page is found not to be auto scrolling and remains static on the page. Steps To reproduce the bug: 1.Open url"automationpractice.com". 2.Home page is loaded. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable scroll the images automatically which is not as expected. | Coding | Google Chrome |  | P1 | High | 1.1.2 | 2 | 24/11/2018 | Bineet Jaiswal | Rajib Ghosh | ACT |  | TC_030 | Bilwa Pelapkar | 26/11/2018 | 26/11/2018 | Bineet Jaiswal
DF_016 | HOME | The sigin button on the home page is found not to be functional. | Detailed Description: The sigin button on the home page is found not to be functional. Steps To reproduce the bug: 1.Open url"automationpractice.com". 2.Home page is loaded. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to navigate user to sigin page which is not as expected. | Coding | Google Chrome |  | P1 | High | 1.1.2 | 2 | 24/11/2018 | Bineet Jaiswal | Rajib Ghosh | ACT |  | TC_034 | Bilwa Pelapkar | 26/11/2018 | 26/11/2018 | Bineet Jaiswal
DF_017 | HOME | The Getting saving now button on the home page is found not to be functional. | Detailed Description: The Get saving now button on the home page is found not to be functional which restricts user to avail any type of discount onthe specific product. Steps To reproduce the bug: 1.Open url"automationpractice.com". 2.Home page is loaded. 3.Click on Getting Saving button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to navigate userto the discount page which is not as expected. | Coding | Google Chrome |  | P1 | High | 1.1.2 | 2 | 24/11/2018 | Bineet Jaiswal | Rajib Ghosh | ACT |  | TC_034 | Bilwa Pelapkar | 26/11/2018 | 26/11/2018 | Bineet Jaiswal